## EI, PH2B - Cycle time
L&T Limited (Realty Division) Emerald Isle Project, Phase 2B Project Tower wise Actual Slab Casting Dates & Cycle Time - Annexure 1
EI, PH2B : SLAB WISE CYCLE TIME (Plan Vs Actual)
Above Terrace Work | Baseline Finish | Cycle Time | Actual Finish | Cycle Time | Baseline Finish | Cycle Time | Actual Finish | Cycle Time | Baseline Finish | Cycle Time | Actual Finish | Cycle Time | Baseline Finish | Cycle Time | Actual Finish | Cycle Time | Baseline Finish | Cycle Time | Actual Finish | Cycle Time | Baseline Finish | Cycle Time | Actual Finish | Cycle Time | Baseline Finish | Cycle Time | Actual Finish | Cycle Time | Baseline Finish | Cycle Time | Actual Finish | Cycle Time | Baseline Finish | Cycle Time | Actual Finish | Cycle Time
Terrace Slab | 2023-02-07 | 22 | 2024-02-01 | 20 | 2023-02-07 | 22 | 2024-02-03 | 18 | 2023-03-01 | 21 | 2024-03-12 | 13 | 2023-03-01 | 21 | 2023-12-15 | 15 | 2023-03-01 | 21 | 2023-12-27 | 17 | 2023-02-13 | 23 | 2023-12-06 | 27 | 2023-02-08 | 22 | 2023-11-24 | 28 | 2023-01-14 | 19 | 2023-09-24 | 28 | 2023-01-14 |  | 2023-09-27 | 27
18th Flr.Slab | [8 empty] | 2023-02-08 | 8 | 2024-02-28 | 6 | 2023-02-08 | 8 | 2023-11-30 | 15 | 2023-02-08 | 8 | 2023-12-10 | 8 | 2023-01-21 | 8 | 2023-11-09 | 14 | 2023-01-17 | 8 | 2023-10-27 | 10 | 2022-12-26 | 9 | 2023-08-27 | 17 | 2022-12-24 |  | 2023-08-31 | 13
17th Flr.Slab | 2023-01-16 | 9 | 2024-01-12 | 13 | 2023-01-16 | 9 | 2024-01-16 | 12 | 2023-01-31 | 10 | 2024-02-22 | 4 | 2023-01-31 | 10 | 2023-11-15 | 14 | 2023-01-31 | 10 | 2023-12-02 | 10 | 2023-01-13 | 8 | 2023-10-26 | 15 | 2023-01-09 | 9 | 2023-10-17 | 9 | 2022-12-17 | 8 | 2023-08-10 | 16 | 2022-12-16 |  | 2023-08-18 | 17
16th Flr.Slab | 2023-01-07 | 8 | 2023-12-30 | 12 | 2023-01-07 | 8 | 2024-01-04 | 14 | 2023-01-21 | 8 | 2024-02-18 | 5 | 2023-01-21 | 8 | 2023-11-01 | 12 | 2023-01-21 | 8 | 2023-11-22 | 11 | 2023-01-05 | 8 | 2023-10-11 | 11 | 2022-12-31 | 8 | 2023-10-08 | 10 | 2022-12-09 | 8 | 2023-07-25 | 14 | 2022-12-08 |  | 2023-08-01 | 17
15th Flr.Slab | 2022-12-30 | 8 | 2023-12-18 | 12 | 2022-12-30 | 8 | 2023-12-21 | 13 | 2023-01-13 | 8 | 2024-02-13 | 6 | 2023-01-13 | 8 | 2023-10-20 | 10 | 2023-01-13 | 8 | 2023-11-11 | 10 | 2022-12-28 | 8 | 2023-09-30 | 10 | 2022-12-23 | 8 | 2023-09-28 | 8 | 2022-12-01 | 9 | 2023-07-11 | 21 | 2022-11-30 |  | 2023-07-15 | 16
14th Flr.Slab | 2022-12-22 | 9 | 2023-12-06 | 18 | 2022-12-22 | 9 | 2023-12-08 | 13 | 2023-01-05 | 9 | 2024-02-07 | 7 | 2023-01-05 | 9 | 2023-10-10 | 10 | 2023-01-05 | 9 | 2023-11-01 | 10 | 2022-12-20 | 10 | 2023-09-20 | 14 | 2022-12-15 | 9 | 2023-09-20 | 15 | 2022-11-22 | 10 | 2023-06-20 | 5 | 2022-11-21 |  | 2023-06-29 | 16
13th Flr.Slab | 2022-12-13 | 10 | 2023-11-18 | 34 | 2022-12-13 | 10 | 2023-11-25 | 22 | 2022-12-27 | 10 | 2024-01-31 | 10 | 2022-12-27 | 10 | 2023-09-30 | 8 | 2022-12-27 | 10 | 2023-10-22 | 8 | 2022-12-10 | 9 | 2023-09-06 | 10 | 2022-12-06 | 10 | 2023-09-05 | 11 | 2022-11-12 | 9 | 2023-06-15 | 11 | 2022-11-11 |  | 2023-06-13 | 12
12th Flr.Slab | 2022-12-03 | 9 | 2023-10-15 | 16 | 2022-12-03 | 9 | 2023-11-03 | 11 | 2022-12-17 | 9 | 2024-01-21 | 9 | 2022-12-17 | 9 | 2023-09-22 | 19 | 2022-12-17 | 9 | 2023-10-14 | 7 | 2022-12-01 | 9 | 2023-08-27 | 11 | 2022-11-26 | 9 | 2023-08-25 | 14 | 2022-11-03 | 9 | 2023-06-04 | 17 | 2022-11-02 |  | 2023-06-01 | 8
11th Flr. Slab | 2022-11-24 | 9 | 2023-09-29 | 15 | 2022-11-24 | 9 | 2023-10-23 | 15 | 2022-12-08 | 9 | 2024-01-12 | 14 | 2022-12-08 | 9 | 2023-09-03 | 12 | 2022-12-08 | 9 | 2023-10-07 | 10 | 2022-11-22 | 10 | 2023-08-16 | 14 | 2022-11-17 | 9 | 2023-08-11 | 11 | 2022-10-25 | 10 | 2023-05-18 | 12 | 2022-10-23 |  | 2023-05-24 | 12
10th Flr.Slab | 2022-11-15 | 10 | 2023-09-14 | 11 | 2022-11-15 | 10 | 2023-10-08 | 16 | 2022-11-29 | 10 | 2023-12-29 | 125 | 2022-11-29 | 10 | 2023-08-22 | 10 | 2022-11-29 | 10 | 2023-09-27 | 8 | 2022-11-12 | 9 | 2023-08-02 | 14 | 2022-11-08 | 10 | 2023-07-31 | 13 | 2022-10-15 | 9 | 2023-05-06 | 9 | 2022-10-14 |  | 2023-05-12 | 9
9th Flr.Slab | 2022-11-05 | 9 | 2023-09-03 | 15 | 2022-11-05 | 9 | 2023-09-22 | 14 | 2022-11-19 | 9 | 2023-08-26 | 19 | 2022-11-19 | 9 | 2023-08-12 | 13 | 2022-11-19 | 9 | 2023-09-19 | 8 | 2022-11-03 | 9 | 2023-07-19 | 12 | 2022-10-29 | 9 | 2023-07-18 | 11 | 2022-10-06 | 9 | 2023-04-27 | 39 | 2022-10-05 |  | 2023-05-03 | 11
8th Flr.Slab | 2022-10-27 | 9 | 2023-08-19 | 11 | 2022-10-27 | 9 | 2023-09-08 | 14 | 2022-11-10 | 9 | 2023-08-07 | 15 | 2022-11-10 | 9 | 2023-07-30 | 13 | 2022-11-10 | 9 | 2023-09-11 | 9 | 2022-10-25 | 10 | 2023-07-07 | 14 | 2022-10-20 | 9 | 2023-07-07 | 16 | 2022-09-27 | 11 | 2023-03-19 | 21 | 2022-09-26 |  | 2023-04-22 | 39
7th Flr.Slab | 2022-10-18 | 10 | 2023-08-08 | 16 | 2022-10-18 | 10 | 2023-08-25 | 11 | 2022-11-01 | 10 | 2023-07-23 | 21 | 2022-11-01 | 10 | 2023-07-17 | 24 | 2022-11-01 | 10 | 2023-09-02 | 15 | 2022-10-15 | 9 | 2023-06-23 | 12 | 2022-10-11 | 10 | 2023-06-21 | 12 | 2022-09-16 | 9 | 2023-02-26 | 7 | 2022-09-15 |  | 2023-03-14 | 12
6th Flr.Slab | 2022-10-08 | 10 | 2023-07-23 | 19 | 2022-10-08 | 10 | 2023-08-14 | 12 | 2022-10-22 | 10 | 2023-07-02 | 16 | 2022-10-22 | 10 | 2023-06-23 | 9 | 2022-10-22 | 10 | 2023-08-18 | 13 | 2022-10-06 | 10 | 2023-06-11 | 11 | 2022-10-01 | 10 | 2023-06-09 | 10 | 2022-09-07 | 11 | 2023-02-19 | 10 | 2022-09-06 |  | 2023-03-02 | 13
5th Flr.Slab | 2022-09-28 | 13 | 2023-07-04 | 21 | 2022-09-28 | 13 | 2023-08-02 | 17 | 2022-10-12 | 12 | 2023-06-16 | 10 | 2022-10-12 | 12 | 2023-06-14 | 10 | 2022-10-12 | 12 | 2023-08-05 | 43 | 2022-09-26 | 13 | 2023-05-31 | 12 | 2022-09-21 | 13 | 2023-05-30 | 17 | 2022-08-27 | 11 | 2023-02-09 | 22 | 2022-08-26 |  | 2023-02-17 | 17
4th Flr.Slab | 2022-09-15 | 12 | 2023-06-13 | 15 | 2022-09-15 | 12 | 2023-07-16 | 16 | 2022-09-30 | 11 | 2023-06-06 | 9 | 2022-09-30 | 11 | 2023-06-04 | 20 | 2022-09-30 | 11 | 2023-06-23 | 15 | 2022-09-13 | 12 | 2023-05-19 | 15 | 2022-09-08 | 12 | 2023-05-13 | 14 | 2022-08-16 | 13 | 2023-01-18 | 17 | 2022-08-13 |  | 2023-01-31 | 19
3rd Flr.Slab | 2022-09-03 | 14 | 2023-05-29 | 16 | 2022-09-03 | 14 | 2023-06-30 | 22 | 2022-09-19 | 16 | 2023-05-28 | 11 | 2022-09-19 | 16 | 2023-05-15 | 21 | 2022-09-19 | 16 | 2023-06-08 | 24 | 2022-09-01 | 14 | 2023-05-04 | 19 | 2022-08-27 | 15 | 2023-04-29 | 21 | 2022-08-03 | 16 | 2023-01-01 | 13 | 2022-08-02 |  | 2023-01-12 | 16
2nd Flr.Slab | 2022-08-20 | 31 | 2023-05-13 | 30 | 2022-08-20 | 31 | 2023-06-08 | 43 | 2022-09-03 | 31 | 2023-05-17 | 22 | 2022-09-03 | 31 | 2023-04-24 | 23 | 2022-09-03 | 31 | 2023-05-15 | 28 | 2022-08-18 | 31 | 2023-04-15 | 25 | 2022-08-12 | 30 | 2023-04-08 | 20 | 2022-07-18 | 32 | 2022-12-19 | 20 | 2022-07-16 |  | 2022-12-27 | 16
1st Flr.Slab | 2022-07-20 | 40 | 2023-04-13 | 125 | 2022-07-20 | 40 | 2023-04-26 | 116 | 2022-08-03 | 40 | 2023-04-25 | 97 | 2022-08-03 | 40 | 2023-04-01 | 71 | 2022-08-03 | 40 | 2023-04-17 | 115 | 2022-07-18 | 40 | 2023-03-21 | 97 | 2022-07-13 | 40 | 2023-03-19 | 102 | 2022-06-16 | 40 | 2022-11-29 | 101 | 2022-06-15 |  | 2022-12-11 | 127
Stilt Flr.Slab - 34.2 | 2022-06-10 | 17 | 2022-12-09 | 18 | 2022-06-10 | 17 | 2022-12-31 | 13 | 2022-06-24 | 17 | 2023-01-18 | 19 | 2022-06-24 | 17 | 2023-01-20 | 23 | 2022-06-24 | 17 | 2022-12-23 | 20 | 2022-06-08 | 18 | 2022-12-14 | 22 | 2022-06-03 | 17 | 2022-12-07 | 37 | 2022-05-07 | 17 | 2022-08-20 | 40 | 2022-05-06 |  | 2022-08-06 | 42
P3 Flr.Slab - 30.9 | 2022-05-24 | 18 | 2022-11-21 | 21 | 2022-05-24 | 18 | 2022-12-18 | 26 | 2022-06-07 | 18 | 2022-12-30 | 30 | 2022-06-07 | 18 | 2022-12-28 | 32 | 2022-06-07 | 18 | 2022-12-03 | 23 | 2022-05-21 | 17 | 2022-11-22 | 32 | 2022-05-17 | 18 | 2022-10-31 | 34 | 2022-04-20 | 19 | 2022-07-11 | 59 | 2022-04-19 |  | 2022-06-25 | 64
P2 Flr.Slab - 27.6 | 2022-05-06 | 21 | 2022-10-31 | 24 | 2022-05-06 | 21 | 2022-11-22 | 20 | 2022-05-20 | 21 | 2022-11-30 | 21 | 2022-05-20 | 21 | 2022-11-26 | 18 | 2022-05-20 | 21 | 2022-11-10 | 15 | 2022-05-04 | 21 | 2022-10-21 | 21 | 2022-04-29 | 21 | 2022-09-27 | 23 | 2022-04-01 | 21 | 2022-05-13 | 42 | 2022-03-31 |  | 2022-04-22 | 38
P1 Flr.Slab - 24.3 | 2022-04-15 | 29 | 2022-10-07 | 41 | 2022-04-15 | 29 | 2022-11-02 | 51 | 2022-04-29 | 29 | 2022-11-09 | 40 | 2022-04-29 | 29 | 2022-11-08 | 41 | 2022-04-29 | 29 | 2022-10-26 | 34 | 2022-04-13 | 29 | 2022-09-30 | 27 | 2022-04-08 | 29 | 2022-09-04 | 64 | 2022-03-11 | 30 | 2022-04-01 | 35 | 2022-03-10 |  | 2022-03-15 | 18
B1 / Tie Beam - 21.0 | 2022-03-17 | 19 | 2022-08-27 | 149 | 2022-03-17 | 19 | 2022-09-12 | 152 | 2022-03-31 | 19 | 2022-09-30 | 23 | 2022-03-31 | 19 | 2022-09-28 | 25 | 2022-03-31 | 19 | 2022-09-22 | 73 | 2022-03-15 | 19 | 2022-09-03 | 56 | 2022-03-10 | 19 | 2022-07-02 | 39 | 2022-02-09 | 20 | 2022-02-25 | 14 | 2022-02-08 |  | 2022-02-25 | 46
PCC + Footings | 2022-02-26 | 38 | 2022-03-31 | 38 | 2022-02-26 | 38 | 2022-04-13 | 35 | 2022-03-12 | 38 | 2022-09-07 | 27 | 2022-03-12 | 38 | 2022-09-03 | 44 | 2022-03-12 | 38 | 2022-07-11 | 44 | 2022-02-24 | 38 | 2022-07-09 | 90 | 2022-02-19 | 38 | 2022-05-24 | 56 | 2022-01-20 | 38 | 2022-02-11 | 46 | 2022-01-19 |  | 2022-01-10 | 23
Towers | T11A |  |  |  | T11B |  | T11B |  | T12A |  | T12A |  | T12B |  | T12B |  | T12C |  | T12C |  | T13A |  | T13A |  | T13B |  | T13B |  | T14A |  | T14A |  | T14B |  | T14B
792

## Concrete qty
Slab/Floors | T11A | T11B | T12A | T12B | T12C | T13A | T13B | T14A | T14B | Total
Raft | 300 | 300 | 500 | 424 | 480 | 270 | 284 | 300 | 300 | 3158
B-2 | [9 empty] | 0
B-1/Tie Beams | 167 | 167 | 93 | 89 | 88 | 56 | 79 | 200 | 200 | 1139
P-1 | 102 | 118 | 156 | 182 | 179 | 102 | 113 | 140 | 150 | 1242
P-2 | 79 | 100 | 109 | 151 | 149 | 85 | 96 | 120 | 120 | 1009
P-3 | 93 | 98 | 108 | 100 | 126 | 102 | 103 | 168 | 180 | 1078
Stilt | 137 | 136 | 190 | 182 | 179 | 114 | 161 | 180 | 161 | 1440
F1 | 135 | 132 | 189 | 175 | 173 | 121 | 150 | 160 | 150 | 1385
F2 | 135 | 132 | 189 | 175 | 173 | 121 | 150 | 160 | 150 | 1385
F3 | 135 | 132 | 189 | 175 | 173 | 121 | 150 | 160 | 150 | 1385
F4 | 143 | 140 | 189 | 175 | 173 | 121 | 150 | 160 | 150 | 1401
F5 | 135 | 132 | 201 | 184 | 182 | 125 | 155 | 165 | 155 | 1434
F6 | 135 | 140 | 189 | 175 | 173 | 121 | 150 | 160 | 150 | 1393
F7 | 135 | 132 | 189 | 184 | 182 | 125 | 150 | 160 | 155 | 1412
F8 | 143 | 140 | 189 | 175 | 173 | 121 | 150 | 160 | 150 | 1401
F9 | 135 | 132 | 189 | 184 | 182 | 125 | 150 | 160 | 155 | 1412
F10 | 135 | 140 | 189 | 175 | 173 | 121 | 150 | 160 | 150 | 1393
F11 | 135 | 132 | 189 | 184 | 182 | 125 | 150 | 160 | 155 | 1412
F12 | 135 | 140 | 201 | 175 | 173 | 121 | 155 | 165 | 150 | 1415
F13 | 135 | 132 | 189 | 184 | 182 | 125 | 150 | 160 | 155 | 1412
F14 | 135 | 140 | 189 | 175 | 173 | 121 | 150 | 160 | 150 | 1393
F15 | 135 | 132 | 189 | 184 | 182 | 125 | 150 | 160 | 155 | 1412
F16 | 135 | 140 | 189 | 175 | 173 | 121 | 150 | 160 | 150 | 1393
F17 | 135 | 132 | 189 | 184 | 182 | 125 | 150 | 160 | 155 | 1412
F18 |  |  | 189 | 175 | 173 | 121 | 150 | 160 | 150 | 1118
Terrace | 135 | 132 | 189 | 175 | 173 | 121 | 150 | 160 | 150 | 1385
Total | 3324 | 3351 | 4771 | 4516 | 4551 | 3056 | 3696 | 4158 | 3996 | 35419

## Consumptions
Equipment Group | Industry Standard | Baseline | Actual | Calculation Step
Entry & Gate Process (min) | 0.5 | 5 | 10
Queue & Parking (min) | 2.5 | 5 | 10
Discharge (6m³)(min) | 25 | 25 | 25
Clean & Exit (min) | 10 | 10 | 10
Total Site Window (min) | 38 | 45 | 55
Site window diesel consumption/hr | 2.5 | 2.5 | 2.5
Diesel conumption/hr for transport distance | 5 | 5 | 5
Average transport distance for RMC plant | 15 | 15 | 15
Total diesel consumption Site Window for total trips | 9346.6806 | 11068.4375 | 13528.0903
Total diesel consumption during transport | 29515.8333 | 29515.8333 | 29515.8333
Total Diesel consumption | 38862.5139 | 40584.2708 | 43043.9236
Carbon emissions (t) @@ 2.68 kg/L | 104.1515 | 108.7658 | 115.3577
| 312 | 406 | 792
Total Site working hours | 9 | 9 | 9
Energy consumtion/hr | 45 | 45 | 45
Utilisation factor for TC | 40% | 40% | 40% | S. Ahlan et al. (2015): Energy consumption of tower cranes in high-rise construction. Studies show that the average power demand of a tower crane is typically 35% to 45% of its connected load.
Utilisation factor for PH | 10% | 10% | 10% | ISO 25745-2: Energy performance of lifts, escalators and moving walks. While for permanent lifts, the "Usage Category" logic applies. For construction hoists (low intensity), a utilization factor of 0.1 is the industry standard for estimating temporary power.
Concrete Pump efficiency | 1.2222 | 1.2222 | 1.4667
Steel yard efficiency | 1.8 | 2 | 3.5
Tower Cranes (4 Nos) | 202176 | 263088 | 513216 | Site Presence * 9h * 45kW * Util
Passenger Hoists (9 Nos) | 12636 | 16443 | 32076 | Tower-Days * 9h * 15kW
Steel Yard (On-site) | 6375.42 | 7083.8 | 12396.65 | MT * (1.8 / 2.0 / 3.5)
Concrete Pumps (4 Nos) | 43289.8889 | 43289.8889 | 51947.8667 | Vc * (1.2 / 1.2 / 1.44)
Total Electricity | 264477.3089 | 329904.6889 | 609636.5167 | Consolidated Power
Carbon emissions (t) @0.82 kg/kWh | 216.8714 | 270.5218 | 499.9019
TOTAL RCC FOOTPRINT | 321.0229 | 379.2877 | 615.2597

## Steel & Shuttering qty
Tower ID | Concrete (m³) | Reinforcement (MT) | Shuttering (m²) | RMC Trips (6m³)
T11A | 3324 | 332.4 | 11634 | 554
T11B | 3351 | 335.1 | 11728.5 | 558.5
T12A | 4771 | 477.1 | 16698.5 | 795.1667
T12B | 4516 | 451.6 | 15806 | 752.6667
T12C | 4551 | 455.1 | 15928.5 | 758.5
T13A | 3056 | 305.6 | 10696 | 509.3333
T13B | 3696 | 369.6 | 12936 | 616
T14A | 4158 | 415.8 | 14553 | 693
T14B | 3996 | 399.6 | 13986 | 666
TOTAL | 35419 | 3541.9 | 123966.5 | 5903.1667

## Ind stds dates
Slab / Level | T11A |  | T11B |  | T12A |  | T12B |  | T12C |  | T13A |  | T13B |  | T14A |  | T14B
Raft Foundation | 30 | 2021-12-31 | 30 | 2021-12-31 | 30 | 2021-12-31 | 30 | 2021-12-31 | 30 | 2021-12-31 | 30 | 2021-12-31 | 30 | 2021-12-31 | 30 | 2021-12-31 | 30 | 2021-12-31
B-1 / Tie Beams | 25 | 2022-01-25 | 25 | 2022-01-25 | 25 | 2022-01-25 | 25 | 2022-01-25 | 25 | 2022-01-25 | 25 | 2022-01-25 | 25 | 2022-01-25 | 25 | 2022-01-25 | 25 | 2022-01-25
Podium P-1 | 21 | 2022-02-15 | 21 | 2022-02-15 | 21 | 2022-02-15 | 21 | 2022-02-15 | 21 | 2022-02-15 | 21 | 2022-02-15 | 21 | 2022-02-15 | 21 | 2022-02-15 | 21 | 2022-02-15
Podium P-2 | 21 | 2022-03-08 | 21 | 2022-03-08 | 21 | 2022-03-08 | 21 | 2022-03-08 | 21 | 2022-03-08 | 21 | 2022-03-08 | 21 | 2022-03-08 | 21 | 2022-03-08 | 21 | 2022-03-08
Podium P-3 | 21 | 2022-03-29 | 21 | 2022-03-29 | 21 | 2022-03-29 | 21 | 2022-03-29 | 21 | 2022-03-29 | 21 | 2022-03-29 | 21 | 2022-03-29 | 21 | 2022-03-29 | 21 | 2022-03-29
Stilt Slab | 18 | 2022-04-16 | 18 | 2022-04-16 | 18 | 2022-04-16 | 18 | 2022-04-16 | 18 | 2022-04-16 | 18 | 2022-04-16 | 18 | 2022-04-16 | 18 | 2022-04-16 | 18 | 2022-04-16
Floor F1 | 25 | 2022-05-11 | 25 | 2022-05-11 | 25 | 2022-05-11 | 25 | 2022-05-11 | 25 | 2022-05-11 | 25 | 2022-05-11 | 25 | 2022-05-11 | 25 | 2022-05-11 | 25 | 2022-05-11
Typical (F2) | 8 | 2022-05-19 | 8 | 2022-05-19 | 8 | 2022-05-19 | 8 | 2022-05-19 | 8 | 2022-05-19 | 8 | 2022-05-19 | 8 | 2022-05-19 | 8 | 2022-05-19 | 8 | 2022-05-19
Typical (F3) | 8 | 2022-05-27 | 8 | 2022-05-27 | 8 | 2022-05-27 | 8 | 2022-05-27 | 8 | 2022-05-27 | 8 | 2022-05-27 | 8 | 2022-05-27 | 8 | 2022-05-27 | 8 | 2022-05-27
Typical (F4) | 8 | 2022-06-04 | 8 | 2022-06-04 | 8 | 2022-06-04 | 8 | 2022-06-04 | 8 | 2022-06-04 | 8 | 2022-06-04 | 8 | 2022-06-04 | 8 | 2022-06-04 | 8 | 2022-06-04
Typical (F5) | 8 | 2022-06-12 | 8 | 2022-06-12 | 8 | 2022-06-12 | 8 | 2022-06-12 | 8 | 2022-06-12 | 8 | 2022-06-12 | 8 | 2022-06-12 | 8 | 2022-06-12 | 8 | 2022-06-12
Typical (F6) | 8 | 2022-06-20 | 8 | 2022-06-20 | 8 | 2022-06-20 | 8 | 2022-06-20 | 8 | 2022-06-20 | 8 | 2022-06-20 | 8 | 2022-06-20 | 8 | 2022-06-20 | 8 | 2022-06-20
Typical (F7) | 8 | 2022-06-28 | 8 | 2022-06-28 | 8 | 2022-06-28 | 8 | 2022-06-28 | 8 | 2022-06-28 | 8 | 2022-06-28 | 8 | 2022-06-28 | 8 | 2022-06-28 | 8 | 2022-06-28
Typical (F8) | 8 | 2022-07-06 | 8 | 2022-07-06 | 8 | 2022-07-06 | 8 | 2022-07-06 | 8 | 2022-07-06 | 8 | 2022-07-06 | 8 | 2022-07-06 | 8 | 2022-07-06 | 8 | 2022-07-06
Typical (F9) | 8 | 2022-07-14 | 8 | 2022-07-14 | 8 | 2022-07-14 | 8 | 2022-07-14 | 8 | 2022-07-14 | 8 | 2022-07-14 | 8 | 2022-07-14 | 8 | 2022-07-14 | 8 | 2022-07-14
Typical (F10) | 8 | 2022-07-22 | 8 | 2022-07-22 | 8 | 2022-07-22 | 8 | 2022-07-22 | 8 | 2022-07-22 | 8 | 2022-07-22 | 8 | 2022-07-22 | 8 | 2022-07-22 | 8 | 2022-07-22
Typical (F11) | 8 | 2022-07-30 | 8 | 2022-07-30 | 8 | 2022-07-30 | 8 | 2022-07-30 | 8 | 2022-07-30 | 8 | 2022-07-30 | 8 | 2022-07-30 | 8 | 2022-07-30 | 8 | 2022-07-30
Typical (F12) | 8 | 2022-08-07 | 8 | 2022-08-07 | 8 | 2022-08-07 | 8 | 2022-08-07 | 8 | 2022-08-07 | 8 | 2022-08-07 | 8 | 2022-08-07 | 8 | 2022-08-07 | 8 | 2022-08-07
Typical (F13) | 8 | 2022-08-15 | 8 | 2022-08-15 | 8 | 2022-08-15 | 8 | 2022-08-15 | 8 | 2022-08-15 | 8 | 2022-08-15 | 8 | 2022-08-15 | 8 | 2022-08-15 | 8 | 2022-08-15
Typical (F14) | 8 | 2022-08-23 | 8 | 2022-08-23 | 8 | 2022-08-23 | 8 | 2022-08-23 | 8 | 2022-08-23 | 8 | 2022-08-23 | 8 | 2022-08-23 | 8 | 2022-08-23 | 8 | 2022-08-23
Typical (F15) | 8 | 2022-08-31 | 8 | 2022-08-31 | 8 | 2022-08-31 | 8 | 2022-08-31 | 8 | 2022-08-31 | 8 | 2022-08-31 | 8 | 2022-08-31 | 8 | 2022-08-31 | 8 | 2022-08-31
Typical (F16) | 8 | 2022-09-08 | 8 | 2022-09-08 | 8 | 2022-09-08 | 8 | 2022-09-08 | 8 | 2022-09-08 | 8 | 2022-09-08 | 8 | 2022-09-08 | 8 | 2022-09-08 | 8 | 2022-09-08
Typical (F17) | 8 | 2022-09-16 | 8 | 2022-09-16 | 8 | 2022-09-16 | 8 | 2022-09-16 | 8 | 2022-09-16 | 8 | 2022-09-16 | 8 | 2022-09-16 | 8 | 2022-09-16 | 8 | 2022-09-16
Typical (F18) |  |  |  |  | 8 | 2022-09-24 | 8 | 2022-09-24 | 8 | 2022-09-24 | 8 | 2022-09-24 | 8 | 2022-09-24 | 8 | 2022-09-24 | 8 | 2022-09-24
Terrace Slab | 15 | 2022-10-01 | 15 | 2022-10-01 | 15 | 2022-10-09 | 15 | 2022-10-09 | 15 | 2022-10-09 | 15 | 2022-10-09 | 15 | 2022-10-09 | 15 | 2022-10-09 | 15 | 2022-10-09
TOTAL DAYS | 304 |  | 304 |  | 312 |  | 312 |  | 312 |  | 312 |  | 312 |  | 312 |  | 312
2021-12-01