## Exc01
|  | Component | Industry Standards | Baseline (75d) | Actual (255) | 366.54 | Mathematical Step / Formula |  | 110 Days | 0%
|  | Trips per Day (Total) | 162.9067 | 98 | 29 | 10 | 35 mins | 35 mins | 64.59 Tonnes | 0%
Primary Reference |  | Trips per Machine (Mc) | 81.4533 | 49 | 14.5 | 5 | 55 mins | 55 mins
Peurifoy’s Construction Planning (Fixed Cycle Constant) |  | Total Cycle Time (min) | 6.6296 | 11.0204 | 37.2414 | 108 | 125 mins | 125 mins
Caterpillar Performance Handbook (Edition 49/Current) Construction Planning, Equipment, and Methods" (McGraw-Hill) |  | Positioning (In) (min) | 1 | 2.5 | 8 | 23.76 | 40 mins | 40 mins
Komatsu Specifications & Application Handbook. CPWD Analysis of Rates (Government of India) |  | Active Loading Time (min) | 5 | 6 | 6 | 6 | 45 mins | 45 mins
Caterpillar Performance Handbook (Edition 49/Current) Construction Planning, Equipment, and Methods" (McGraw-Hill) |  | Positioning (Out) (min) | 1 | 2.5 | 10 | 29.16 | 90 mins | 90 mins
Shingo’s Seven Wastes (Muda) / Lean Construction Theory |  | Idle Wait Waste (min) | 0 | 0.020408 | 13.2414 | 49.08 | 65 mins | 65 mins
[7 empty] | 40 mins | 40 mins
?? SYSTEM SIMULATION EVALUATION ANALYSIS: • Operational Scope: Modeling a sequential cycle of 200 shore piles under an evaluated schedule constraint of 15 work hours per day. ?? Optimization Bottleneck: High concrete idling delay (90 mins) identified. Toggling JIT to 'Y' is strongly advised to resolve material delivery constraints.

## Exc02
Activity | Total Area (m2) | Depth (m) | Total Qty (Cum.) |  |  | Baseline Start | Baseline Finish | Baseline duration (days) | Daily output req. | Daily trips (10m3/truck) | Actual Start | Actual Finish | Actual duration (days) | Actual Daily output | Daily trips (10m3/truck)
|  |  | Soil | Rock | Total
Excavation | 6109 | 12 | 25657.8 | 47650.2 | 73308 | 2021-12-01 | 2022-02-15 | 75 | 977.44 | 97.744 | 2021-12-01 | 2022-08-13 | 255 | 287.4824 | 28.7482
|  |  | 0.15 | 0.4
| Industry Standards | Baseline considered | Actual achieved |  |  |  |  | 22908.75
Total Trips/day | 162.9067 | 97.744 | 28.7482 |  | 1629.0667 | 45
Work shift (8-6pm, 1 hr lunch) | 9 | 9 | 9
Trips/hour | 17.1429 | 11 | 4
Nos. of Excavators | 2 | 2 | 2
Trucks attended / excavator / hour | 8.5714 | 5.5 | 2
|  | Entry & Park | Loaded | Exit | Waiting
Total time for each truck (1. Entry 2. Loaded 3. Exit) | 11 | 2.5 | 6 | 2.5 | - | Baseline |  | 540 | 14.5 | 37.2414 | 13.2
| 7 | 1 | 5 | 1 | - | Industry standards with ideal logistics |  |  | 29 | 74.4828 | 26.4 | 765.6 | 12.76 | 6.38
| 30 |  |  |  |  | Actual

## Exc03
Parameter | Value | Unit | Logic / Source
Total Excavation Quantity | 73308 | m³ | Area*Depth = 6109sqm * 12 | 290 | 252.7862
Soil Volume | 25658 | m³ | 35% of total | 300 | 244.36
Rock Volume (Basalt) | 47650 | m³ | 65% of total
Truck Capacity | 10 | m³/trip | Standard Indian Tipper
Total Required Trips | 7331 | Nos. | 73,308 / 10
Working Shift | 9 | Hours | 09:00 AM to 06:00 PM
Total Shift Minutes | 540 | Minutes | 9 hrs * 60 mins
No. of Excavators | 2 | Units | 20-ton class
Round Trip Distance | 15 | km | Lead to dumping site
Diesel Emission Factor | 2.68 | kgCO2e/L | IPCC/ICE Database
Grid Emission Factor | 0.82 | kgCO2e/kWh | CEA Indian Grid Factor
Excavator Idle Fuel Rate | 4.5 | L/hr | Engine-on, no-load (Wait/Pos)
Truck Idle Fuel Rate | 2.5 | L/hr | Congestion crawl/Gate wait

## Exc04
Fuel consumption (Excavators in L)
Metric | Industry Standards | Baseline | Actual | Mathematical Step / Formula
Productive Work Fuel | 22908.75 | 22908.75 | 22908.75 | Fixed Work Load (Soil*0.15L/m3 + Rock*0.4L/m3)
Idle Duration / Day / Mc (hrs) | 0 | 0.033333 | 6.4 | (Total Cycle - Loading Time) / 60
Total Idle Hours | 0 | 5 | 3264 | Idle hrs * Duration (Days) * 2 Mc
Idle Fuel Waste | 0 | 22.5 | 14688 | Total Idle Hours * 4.5 L/hr
Total Diesel Consumed | 22908.75 | 22931.25 | 37596.75 | Work Fuel + Idle Waste
Fuel Consumption (Trucks in L)
Metric | Industry Standards | Baseline | Actual | Mathematical Step / Formula
Standard Transport Fuel | 36655 | 36655 | 36655 | 7,331 trips * (15km / 3km per L)
Traffic Penalty | 0 | 0 | 14662 | 7,331 trips * 2.0 L (Crawl Waste)
Total Fleet Diesel | 36655 | 36655 | 51317 | Standard + Traffic Penalty
Carbon Estimations (in Tonnes)
Category | Industry Standards | Baseline | Actual | Mathematical Step / Formula
Excavator Carbon | 61.3954 | 61.4557 | 100.7593 | Total Fuel * 2.68 / 1000
Truck Fleet Carbon | 98.2354 | 98.2354 | 137.5296 | Total Fuel * 2.68 / 1000
Site Grid Load | 4.9815 | 8.3025 | 28.2285 | Days * 15kWh * 0.82 / 1000
Total Carbon Net impact | 164.6124 | 167.9937 | 266.5174 | Sum of all categories
Net Variance |  | - | 98.5237 | Actual - Baseline

## Dashboard Data
Phase | Activity Component | Scenario Case | Duration/Time (Mins) | Phase Total Days | Phase Carbon Tonnage
1. Shore Piling | 1. Rig Positioning | Industry Std | 10 | 45 | 24.3027
1. Shore Piling | 1. Rig Positioning | Baseline | 15 | 60 | 33.3253
1. Shore Piling | 1. Rig Positioning | Actual Case | 35 | 110 | 64.592
1. Shore Piling | 2. Boring (Soil) | Industry Std | 30 | 45 | 24.3027
1. Shore Piling | 2. Boring (Soil) | Baseline | 40 | 60 | 33.3253
1. Shore Piling | 2. Boring (Soil) | Actual Case | 55 | 110 | 64.592
1. Shore Piling | 3. Boring (Rock) | Industry Std | 60 | 45 | 24.3027
1. Shore Piling | 3. Boring (Rock) | Baseline | 80 | 60 | 33.3253
1. Shore Piling | 3. Boring (Rock) | Actual Case | 125 | 110 | 64.592
1. Shore Piling | 4. Cleaning & Flushing | Industry Std | 15 | 45 | 24.3027
1. Shore Piling | 4. Cleaning & Flushing | Baseline | 20 | 60 | 33.3253
1. Shore Piling | 4. Cleaning & Flushing | Actual Case | 40 | 110 | 64.592
1. Shore Piling | 5. Cage Lowering | Industry Std | 15 | 45 | 24.3027
1. Shore Piling | 5. Cage Lowering | Baseline | 20 | 60 | 33.3253
1. Shore Piling | 5. Cage Lowering | Actual Case | 45 | 110 | 64.592
1. Shore Piling | 6. RMC Wait Lag | Industry Std | 5 | 45 | 24.3027
1. Shore Piling | 6. RMC Wait Lag | Baseline | 20 | 60 | 33.3253
1. Shore Piling | 6. RMC Wait Lag | Actual Case | 90 | 110 | 64.592
1. Shore Piling | 7. Concreting Work | Industry Std | 35 | 45 | 24.3027
1. Shore Piling | 7. Concreting Work | Baseline | 45 | 60 | 33.3253
1. Shore Piling | 7. Concreting Work | Actual Case | 65 | 110 | 64.592
1. Shore Piling | 8. Rig Shifting | Industry Std | 10 | 45 | 24.3027
1. Shore Piling | 8. Rig Shifting | Baseline | 15 | 60 | 33.3253
1. Shore Piling | 8. Rig Shifting | Actual Case | 40 | 110 | 64.592
2. Mass Excavation | 1. Inbound Positioning | Industry Std | 1 | 45 | 164.6124
2. Mass Excavation | 1. Inbound Positioning | Baseline | 2.5 | 75 | 167.9937
2. Mass Excavation | 1. Inbound Positioning | Actual Case | 8 | 255 | 266.5174
2. Mass Excavation | 2. Shovel Loading Time | Industry Std | 5 | 45 | 164.6124
2. Mass Excavation | 2. Shovel Loading Time | Baseline | 6 | 75 | 167.9937
2. Mass Excavation | 2. Shovel Loading Time | Actual Case | 6 | 255 | 266.5174
2. Mass Excavation | 3. Outbound Positioning | Industry Std | 1 | 45 | 164.6124
2. Mass Excavation | 3. Outbound Positioning | Baseline | 2.5 | 75 | 167.9937
2. Mass Excavation | 3. Outbound Positioning | Actual Case | 10 | 255 | 266.5174
2. Mass Excavation | 4. Idle Wait Waste | Industry Std | 0 | 45 | 164.6124
2. Mass Excavation | 4. Idle Wait Waste | Baseline | 0.020408 | 75 | 167.9937
2. Mass Excavation | 4. Idle Wait Waste | Actual Case | 13.2414 | 255 | 266.5174

## Shore Piling
Depth | 18
Diameter | 750
Gap b/w piles | 150
Total distance | 900
Total piles | 200
Baseline duration | 60
Total piling RMT | 3600
Productivity | 60
Piles /day | 3.3333
Total days | 45 | 60 | 110
Event Component | Industry Std (45d) | Baseline (60d) | Actual (110d)
Rig Positioning | 10 | 15 | 35
Boring (0-8m Soil) | 30 | 40 | 55
Boring (8-18m Rock) | 60 | 80 | 125
Cleaning & Flushing | 15 | 20 | 40
Cage Lowering | 15 | 20 | 45
RMC Wait Lag | 5 | 20 | 90
Concreting (9.14m³) | 35 | 45 | 65
Rig Shifting | 10 | 15 | 40
Total Cycle / Pile | 180 | 255 | 495
Working fuel | 8433.3333 | 11366.6667 | 18700
Idle Fuel | 433.3333 | 866.6667 | 5200
Electricity usage/h (duty factor - 0.4 ) | 12 | 12 | 12
Total carbon (Tonnes) | 24.3027 | 33.3253 | 64.592
Carbon/pile(kg) | 121.5133 | 166.6267 | 322.96
Idle Waste Factor | 4.887% | 7.084% | 21.76%

## DB - Shore piling
Column B (Component/Label) | Column C (User Input) | Column D (Dynamic Logic Formula) | Column E (Thesis Academic Reference Formula) | [5 empty] | Column L (Simulated Absolute Output) | Column M (Relative Variance Change %)
Select Scenario (1=Std, 2=Base, 3=Actual): | 3 |  |  | Operational Activity Step | Baseline Duration | Lean Optimized Duration |  | Simulated Project Duration: | 110 Days | 0%
|  |  |  | 1. Rig Positioning | 10 mins | 35 mins | 35 mins | Net Carbon Footprint: | 64.59 Tonnes | 0%
Enable Value Stream Mapping (VSM)? (Y/N): | N | VSM Inactive: Maintaining standard historical logistical waste loops. |  | 2. Boring (0-8m Soil) | 30 mins | 55 mins | 55 mins
Enable Just-In-Time (JIT)? (Y/N): | N | JIT Inactive: Mixed truck fleets run uncoordinated, causing material logjams. |  | 3. Boring (8-18m Rock) | 60 mins | 125 mins | 125 mins
Enable Parallel Processing? (Y/N): | N | Parallelism Inactive: Linear sequencing causes execution bottlenecks. |  | 4. Cleaning & Flushing | 15 mins | 40 mins | 40 mins
|  |  |  | 5. Cage Lowering | 15 mins | 45 mins | 45 mins
|  |  |  | 6. RMC Wait Lag | 5 mins | 90 mins | 90 mins
|  |  |  | 7. Concreting Work | 35 mins | 65 mins | 65 mins
|  |  |  | 8. Rig Shifting | 10 mins | 40 mins | 40 mins
?? PILING OPERATIONAL SYSTEM SIMULATION EVALUATION: • Operational Scope Footprint: Simulating sequential cycle execution parameters across 200 units under a schedule constraint of 15 work hours/day. ?? Logistical Bottleneck: High concrete wait idling lag (90 mins) identified. Toggle Just-In-Time (JIT) to 'Y' to resolve material delivery constraints.
RUN SIMULATION

## Excavation
1. MASTER PROJECT EARTHWORKS PARAMETERS
Total Excavation Quantity | 73308 | m³ | Area * Depth = 6109 sqm * 12m
Soil Volume Component (35%) | 25657.8 | m³ | High-level excavation stratum layer
Rock Volume Component - Basalt (65%) | 47650.2 | m³ | Tough stratum requiring slow tool-on-face work
Dump Truck Tipper Capacity | 10 | m³/trip | Standard Indian Tipper Volume capacity
Total Required Disposal Trips | 7330.8 | Nos. | Total Qty / 10m³ capacity bucket
Standard Working Shift Duration | 9 | Hours | 09:00 AM to 06:00 PM (1 hr lunch loop)
Shift Duration in Minutes | 540 | Minutes | 9 Hours * 60 minutes
Active Excavator Fleet Size | 2 | Units | 20-ton class heavy earthmovers
Round-Trip Haul Distance | 15 | km | Site coordinates to designated dump yard
Diesel Emission Intensity Factor | 2.68 | kgCO2e/L | IPCC National Greenhouse Gas Inventory
Grid Electricity Emission Factor | 0.82 | kgCO2e/kWh | Central Electricity Authority (CEA India)
Excavator Idle Fuel Burn Rate | 4.5 | L/hr | Engine on, zero-load wait cycles
Truck Idle Fuel Burn Rate | 2.5 | L/hr | Site gate traffic crawl congestion lag
2. PROJECT CALENDAR TIMELINE KPI | Industry Std. | Baseline | Actual
Planned Execution Duration (Days) | 45 | 75 | 255
Required Daily Output Volume (m³) | 1629.0667 | 977.44 | 287.4824
Required Disposal Trips per Day (Total) | 162.9067 | 97.744 | 28.7482
3. FLEET LOGISTICS CYCLE TIMES | Industry Std. | Baseline | Actual
Trips per Day (Total Fleet) | 162.9067 | 97.744 | 28.7482 | Trips/Day
Handled Trips per Single Excavator | 81.4533 | 48.872 | 14.3741 | Trips/Mc
Total Shovel Cycle Turnaround Time | 7 | 11.0204 | 37.2414 | Minutes
Truck Positioning Lag - Inbound | 1 | 2.5 | 8 | Minutes
Active Excavator Loading Work Time | 5 | 6 | 6 | Minutes
Truck Positioning Lag - Outbound | 1 | 2.5 | 10 | Minutes
Machinery Idle Wait Duration per Day | 0 | 0.020408 | 13.2414 | Hours/Mc
4. ENERGY & CARBON ACCOUNTING
Fixed Productive Excavator Work Fuel | 22908.75 | 22908.75 | 22908.75 | Liters
Excavator Idling Fuel Waste Volume | 0 | 22.5 | 14688 | Liters
Net Excavator Diesel Volume (Total) | 22908.75 | 22931.25 | 37596.75 | Liters
Standard Truck Transport Fuel Volume | 36655 | 36655 | 36655 | Liters
Traffic Congestion Crawl Fuel Waste | 0 | 0 | 14662 | Liters
Net Dump Truck Diesel Volume (Total) | 36655 | 36655 | 51317 | Liters
Site Office Grid Electricity Usage | 4.9815 | 8.3025 | 28.2285 | kWh
Total Environmental Carbon Net Impact | 164.6124 | 167.9937 | 266.5174 | Tonnes CO2

## DB - Excavation
Select Excavation Scenario (1=Std, 2=Base, 3=Actual) | 3 |  | Fleet Logistics Cycle Component | Baseline Time | Lean Optimized Duration | 0 Days | 255 Days | 0%
|  |  | Truck Positioning Lag (In-Bound) | 8 mins | 8 mins | 0 L | 37597 L | 0%
Optimize Haul Routing (VSM)? (Y/N) | N | VSM Inactive: Trucks queue in severe site traffic bottlenecks, burning extra congestion fuel. | Active Excavator Loading Work Time | 6 mins | 6 mins | 0 L | 51317 L | 0%
Match-Factor Balancing (JIT)? (Y/N) | N | JIT Inactive: Fleet mismatch causes excavation rigs to cycle completely idle waiting for tippers. | Truck Positioning Lag (Out-Bound) | 10 mins | 10 mins | 0 kWh | 34425 kWh | 0%
|  |  | 4. Excavator Idle Wait Waste | 13.24 mins | 13.24 mins | 0 Tonnes | 266.52 Tonnes | 0%
|  |  | Total Shovel Cycle Turnaround Time: | 37.24 mins | 37.24 mins
?? EARTHWORKS FLEET LOGISTICS SIMULATION REPORT: • Project Workload Scope: Simulating earthmoving cycles for 7331 disposal trips utilizing a heavy fleet of 2 excavators. ?? FLEET MISMATCH COEFF: Excavators suffer 13.24 mins of idle queue time per load loop due to truck haul synchronization latency. ?? CONGESTION LATENCY: Severe haul route bottlenecks generate an extra 2.0 L/trip traffic penalty across the tipper fleet. ?? STRATEGY DIRECTION: System running at standard un-optimized baseline. Toggle VSM or JIT to 'Y' to simulate lean deployment paths.
RUN SIMULATION